School Year Timelines

Request for Proposal (RFP) For Food Service Management Company (FSMC) Contract

Failure to meet any listed deadline dates will result in the termination of the RFP process. The School Food Authority is required to complete the entire process by July 1.

November 1	Hawaii Child Nutrition Program (HCNP) will notify School Food Authorities (SFA) to provide a written notification of intent to procure Food Service Management Company (FSMC) services or if the SFA is rebidding their existing FSMC contract.

December 1	Deadline for SFA’s to notify HCNP in writing of the SFA’s intent to procure FSMC services or to rebid an existing FSMC contract. HCNP will provide a prototype FSMC contract to the SFA and training.

January 31	Deadline for SFA’s submission of FSMC proposed RFP to HCNP including SFAs bid protest procedures for written approval.

February 28 	Written approval or rejection of RFP sent by HCNP. The SFA MUST receive OHCNP approval prior to publicizing RFP.

March 15	Deadline for first publication date for Public Notice of Release of RFP in Statewide Newspaper (Advertise allowing at least 60 days prior to the date the proposals are due.)

March 15	Deadline for formal release of RFP by SFA to FSMCs registered with HCNP.

March 31	Deadline for FSMC vendors to submit written questions concerning RFP to SFA for written response in form of addendum on April 20.

April 5	Deadline for FSMC to notify SFA of intent to attend SFA Pre-Bid Meeting.

April 15	SFA holds Pre-bid Meeting with all interested HCNP Registered FSMCs with public walk through of campuses, food preparation, and serving sites.

April 20	SFA provides written response to all RFP questions received from all Bidders. SFA written response is in form of an addendum to RFP.

April 30	FSMCs submit written questions arising from Pre-Bid Meeting to SFA.

May 5	SFA sends written response to Pre-Bid Meeting questions to all potential bidders in form of an addendum to RFP.

May 15	Deadline for opening of bids submitted to SFA. (60 days after bid advertised.)

May 31	Submit final recommendation for RFP award and ALL bid responses to HCNP for WRITTEN final approval BEFORE contract award. This includes FSMC contract extensions. SFAs may extend the contract up to four (4) times.

June 15	SFA must obtain final written approval from HCNP prior to submitting contract recommendation to the School Board for their approval.

July 1	Award Bid (On or Before July 1). Requires School Board approval prior to Bid Award.  SFA to provide written award notice to successful FSMC Contractor to procure food, train staff, and implement business plan after School Board approval and after all parties sign the contract.

July 1 - June 30 		Effective dates first year FSMC contracts and contract extensions.

This institution is an equal opportunity provider.